## Sprint 2 backlog
SPRINT 2 BACKLOG
Team QWERTY ¦ Sprint 2 of 2 ¦ 2-13 November 2026 ¦ Ends Friday 13 November ¦ Standups every Monday, Wednesday, and Friday ¦ Planned 113 hours ¦ Day 15 buffer = 0 ¦ Status To-Do until that meeting's Definition of Done
ID | User Story | Tasks | Owner | Status | Estimated effort | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15
US9a | Edit a logged donation: Given a donor owns a donation that is still queued or matched, when they change the food lines, quantity, expiry, or pickup window, then PATCH /api/donations/:id saves the log, restores the previous food-bank capacity, and runs matching again. After picked_up or delivered, the edit is locked with 409. | Build donor edit form at /donations/[id]/edit | PRATANIN KAHTEPMUD | To-Do | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Implement PATCH /api/donations/:id with capacity restore and rematch | JIRATHIWAT SUNTIPREEDATHAM | To-Do | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | QA edit before pickup and 409 after pickup | SAKKARAJ TUVAJIT | To-Do | 4 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US9b | Send one log to many food banks: Given a donor puts one or more foods on a single donation, when splitAcrossBanks is true and the total kilograms exceed one bank, then proposeMatches assigns quantityKg across every in-range bank that still has room, and the sum of quantityKg equals the donation quantity. | Add multi-food lines and the split checkbox on the donor form | PRATANIN KAHTEPMUD | To-Do | 6 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Implement proposeMatches so one donation splits across food banks | SIRAPASSORN POKASERMSONG | To-Do | 8 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Subtract quantityKg from each bank remainingCapacityKg | JIRATHIWAT SUNTIPREEDATHAM | To-Do | 6 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | QA one log to many banks (sum of quantityKg, at least two matches) | SAKKARAJ TUVAJIT | To-Do | 4 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US3b | Expiry alerts at 24, 12, and 2 hours: Given a logged donation, when hours until expiry cross 24, 12, or 2, then a notification is stored for staff and for drivers and shown on /notifications. | Build 24/12/2 hour expiry notification job | JIRATHIWAT SUNTIPREEDATHAM | To-Do | 6 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Render expiry alerts on /notifications | PRATANIN KAHTEPMUD | To-Do | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Emit driver-audience notifications for the same thresholds | SIRAPASSORN POKASERMSONG | To-Do | 4 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | QA alert thresholds and read state | SAKKARAJ TUVAJIT | To-Do | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US4a | Operations dashboard: Given a signed-in user opens /dashboard, when they filter by donor, food bank id, or status, then GET /api/dashboard shows open, matched, picked up, delivered, and urgent counts. | Build operations board filters | PRATANIN KAHTEPMUD | To-Do | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
|  | Implement GET /api/dashboard summary | JIRATHIWAT SUNTIPREEDATHAM | To-Do | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0
|  | QA dashboard counts and filters | SAKKARAJ TUVAJIT | To-Do | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0
US4b | Driver activity log: Given a food bank or logistics user opens /drivers, when GET /api/drivers/activity runs, then each driver shows accepted, picked up, and delivered counts plus recent runs. | Implement GET /api/drivers/activity | SIRAPASSORN POKASERMSONG | To-Do | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0
|  | Build the driver activity page | PRATANIN KAHTEPMUD | To-Do | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0
|  | QA activity counts after pickup and delivery | SAKKARAJ TUVAJIT | To-Do | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0
US5b | Monthly tax summary: Given a donor or logistics user on /receipts, when they export a month, then GET /api/reports/tax returns a CSV or a PDF. This stays Sprint 2 and is not Sprint 1 Done. | Implement monthly tax CSV and PDF | JIRATHIWAT SUNTIPREEDATHAM | To-Do | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 0 | 0 | 0
|  | Add Export CSV and Export PDF on the receipts page | PRATANIN KAHTEPMUD | To-Do | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0
|  | QA tax export for the selected month | SAKKARAJ TUVAJIT | To-Do | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0
US7 | Driver GPS ping: Given a driver, when they POST /api/drivers/location with lat and lng, then the ping is stored and shown on the driver activity log within one minute. | Implement POST /api/drivers/location | SIRAPASSORN POKASERMSONG | To-Do | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0
|  | Show the latest ping on /drivers | PRATANIN KAHTEPMUD | To-Do | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0
|  | QA ping timestamp and coordinates | SAKKARAJ TUVAJIT | To-Do | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
US8 | Decay research spike: Given a donation id, when GET /api/decay?donationId= runs, then the response includes hoursRemaining and a heuristic riskScore. This is not a trained model. | Implement GET /api/decay heuristic | JIRATHIWAT SUNTIPREEDATHAM | To-Do | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0
|  | QA decay response shape | SAKKARAJ TUVAJIT | To-Do | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
|  |  |  | TOTAL | 113 | 7 | 7 | 9 | 9 | 8 | 10 | 6 | 9 | 8 | 8 | 7 | 9 | 10 | 6 | 0
Planning sheet for Sprint 2. New stories US9a (donor edits a log) and US9b (one log sent to many food banks) are first. Then US3b, US4a, US4b, US5b, US7, US8. Meetings: Mon 2 Nov kickoff; Wed 4 (Days 1-2, 14h); Fri 6 (Days 3-4, 18h); Mon 9 (Days 5-7, 24h); Wed 11 (Days 8-9, 17h); Fri 13 close (Days 10-14, 40h). The sprint ends Friday 13 November. Day 15 = 0. 14+18+24+17+40 = 113. Do not mark Done before that card's QA and Definition of Done. Sprint 1 stories stay Done and are not rebuilt.

## Standup map
SPRINT 2 — STANDUP MAP (Monday, Wednesday, Friday)
Meeting | When | Script | Hour-days | Hours | Board after the meeting
1 | Mon 2 Nov 2026 | sprint-2-scrum-meeting-1.md | Kickoff. Day 1 starts after. | 0 | Plans and risks. Every card To-Do. No build hours in the meeting.
2 | Wed 4 Nov 2026 | sprint-2-scrum-meeting-2.md | Days 1-2 | 14 | US9a form 6/6 In Review. PATCH 8/8 In Review. QA not started. US9b still To-Do.
3 | Fri 6 Nov 2026 | sprint-2-scrum-meeting-3.md | Days 3-4 | 18 | US9a QA 4/4 In Review. US9b form 6/6 and proposeMatches 8/8 In Review. Capacity and US9b QA still To-Do.
4 | Mon 9 Nov 2026 | sprint-2-scrum-meeting-4.md | Days 5-7 | 24 | US9a and US9b can move to Done if DoD passes. US3b job 6/6 and driver alerts 4/4. Alerts page 2/4. Dashboard filters 2/6.
5 | Wed 11 Nov 2026 | sprint-2-scrum-meeting-5.md | Days 8-9 | 17 | US3b QA 3/3 In Review. Dashboard API 5/5. Filters 6/6. Activity API 3/6. US5b, US7, US8 still To-Do.
6 | Fri 13 Nov 2026 | sprint-2-scrum-meeting-6.md | Days 10-14 (Day 15 = 0) | 40 | Close. Finish US4a, US4b, US5b, US7, US8. 8 of 8 Done only if DoD passes. Planned 113. Day 15 buffer is 0. No standup after Friday 13.
Hours in each standup window (same cells as the Day 1-15 table). Meeting 1 is the kickoff and logs 0.
Person | M2 D1-2 | M3 D3-4 | M4 D5-7 | M5 D8-9 | M6 D10-14 close | Sprint total
Pratanin | 6 | 6 | 4 | 6 | 10 | 32
Jirathiwat | 8 | 0 | 12 | 5 | 9 | 34
Sirapassorn | 0 | 8 | 4 | 3 | 9 | 24
Sakkaraj | 0 | 4 | 4 | 3 | 12 | 23
TOTAL | 14 | 18 | 24 | 17 | 40 | 113