## Sprint 1 Backlog
SPRINT 1 BACKLOG — CONCLUSION
Team QWERTY ¦ 14–23 October 2026 ¦ 7 of 7 Sprint 1 stories Done ¦ Actual 114 / Planned 114 hours ¦ Remaining 0 ¦ No carry-over to Sprint 2
ID | User Story | Tasks | Owner | Status | Estimated effort | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15
US1a | Log a donation: Given a donor, when they submit food type, quantity, and expiry date/time, then the donation appears in the matching queue within 1 minute. | Build donation entry form UI | PRATANIN KAHTEPMUD | Done | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Implement donation queue ingestion backend logic | JIRATHIWAT SUNTIPREEDATHAM | Done | 8 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | QA test donation creation and queue timing | SAKKARAJ TUVAJIT | Done | 4 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US1b | Auto-match donation to a food bank: Given an open donation, when a food bank within delivery range has reported capacity, then the system proposes a match within 2 minutes. | Develop matching algorithm proximity scoring | SIRAPASSORN POKASERMSONG | Done | 12 | 0 | 0 | 4 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Develop matching algorithm food bank capacity check | JIRATHIWAT SUNTIPREEDATHAM | Done | 8 | 0 | 0 | 0 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Integrate matching service with queue triggers | PRATANIN KAHTEPMUD | Done | 12 | 0 | 0 | 0 | 4 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | QA test auto-matching performance and criteria | SAKKARAJ TUVAJIT | Done | 8 | 0 | 0 | 0 | 0 | 2 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US6 | Select a pickup time window: Given a donor is logging a donation, when they choose a pickup time window from available slots, then the window is attached to the donation record and shown on driver dispatch feeds. | Add pickup time window UI component | PRATANIN KAHTEPMUD | Done | 5 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Connect time window selection to dispatch feed | JIRATHIWAT SUNTIPREEDATHAM | Done | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | QA test time slot validation and feed updates | SAKKARAJ TUVAJIT | Done | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US2a | Track pickup status: Given a matched donation, when a driver marks it "Picked Up," then the timestamp and driver ID are recorded and visible to the receiving food bank. | Build driver pickup endpoint and status update logic | SIRAPASSORN POKASERMSONG | Done | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
|  | Update food bank view to display pickup details | PRATANIN KAHTEPMUD | Done | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
|  | QA test pickup status transition and notifications | SAKKARAJ TUVAJIT | Done | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
US2b | Track delivery status with proof: Given a picked-up donation, when a driver marks it "Delivered," then a delivery timestamp and digital proof (photo or signature) are attached to the donation record. | Build delivery confirmation API with photo or signature attachment | SIRAPASSORN POKASERMSONG | Done | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 4 | 0 | 0 | 0 | 0
|  | Render delivery proof & timestamp in food bank portal | PRATANIN KAHTEPMUD | Done | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0
|  | QA end-to-end delivery confirmation and proof upload | SAKKARAJ TUVAJIT | Done | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0
US5a | Generate automatic digital donation receipt: Given a donation marked "Delivered," when delivery is confirmed, then a digital receipt with recorded weight, food type, and timestamp is auto generated and emailed to the donor. | Implement PDF receipt generation (weight, food type, timestamp) and email service | JIRATHIWAT SUNTIPREEDATHAM | Done | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0
|  | QA test receipt content (weight, food type, timestamp) and email deliverability | SAKKARAJ TUVAJIT | Done | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0
US3a | Check and flag expiry dates: Given a logged donation, when its expiry date is within 24 hours, then it is automatically flagged "urgent" in the matching queue. | Build expiry date monitor background job | JIRATHIWAT SUNTIPREEDATHAM | Done | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 0 | 0
|  | QA test urgent status flagging triggers | SAKKARAJ TUVAJIT | Done | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0
|  |  |  | TOTAL | 114 | 4 | 8 | 10 | 12 | 12 | 13 | 9 | 7 | 6 | 9 | 9 | 6 | 7 | 2 | 0
Sprint 1 conclusion. Same W02 columns as the planning sheet (ID, User Story, Tasks, Owner, Status, Estimated effort, Day 1–15). Day cells are actual hours logged and match the Daily Scrum scripts: Meeting 3 = Day 2 (8h); Meeting 4 = Days 3–4 (22h); Meeting 5 = Days 5–8 (41h); Meeting 6 = Days 9–14 (39h); Day 1 (4h) is Meeting 2; Day 15 buffer is 0. Status is Done after Meeting 6 DoD. Remaining effort is 0. See sheet Standup map. This Done column is the Friday 23 October result after Meeting 6. On Friday 16 October (Meeting 3) the live board is Day 2 only. Sprint 2 stories (US3b, US4a, US4b, US5b, US7, US8) stay on the product backlog.

## Standup map
SPRINT 1 — STANDUP MAP (W02 Day 1–15 aligned to Daily Scrum scripts)
Meeting | When | Script | Hour-days | Hours | Accomplished in that window (board after the meeting)
1 | Wed 14 Oct 2026 | sprint-1-scrum-meeting-1.pdf | Kickoff. Day 1 starts after. | 0 | Plans and risks for US1a. No build hours in the meeting.
2 | Template | sprint-1-scrum-meeting-2.pdf | Day 1 | 4 | Pratanin form 4 of 8h.
3 | Fri 16 Oct 2026 | sprint-1-scrum-meeting-3.md | Day 2 | 8 | Form 8/8 In Review. Ingestion 4/8 In Progress. Sirapassorn 0. Sakkaraj 0.
4 | Mon 19 Oct 2026 | sprint-1-scrum-meeting-4.md | Days 3–4 | 22 | Ingestion 8/8. US1a QA 4/4 In Review. Proximity 7/12. Capacity 3/8. Integrate 4/12. US6 still To-Do.
5 | Wed 21 Oct 2026 | sprint-1-scrum-meeting-5.md | Days 5–8 | 41 | US1a Done. US1b 40/40. US6 13/13. US2a pickup 2/4 In Progress. Incoming, US2b, US5a, US3a To-Do.
6 | Fri 23 Oct 2026 | sprint-1-scrum-meeting-6.md | Days 9–14 (Day 15 = 0) | 39 | Finish US2a, US2b, US5a, US3a. All 7 Sprint 1 stories Done. Actual 114 / planned 114. Remaining 0.
Hours logged by person in each standup window (same cells as the W02 Day 1–15 table)
Person | M2 Day 1 | M3 Day 2 | M4 Days 3–4 | M5 Days 5–8 | M6 Days 9–14 | Sprint total
Pratanin | 4 | 4 | 4 | 13 | 8 | 33
Jirathiwat | 0 | 4 | 7 | 10 | 8 | 29
Sirapassorn | 0 | 0 | 7 | 7 | 12 | 26
Sakkaraj | 0 | 0 | 4 | 11 | 11 | 26
TOTAL | 4 | 8 | 22 | 41 | 39 | 114
Today is Friday 16 October (Meeting 3): live board is Day 2 only. Meeting 4 must not say US6 is built (Days 6-8, Meeting 5). Meeting 5 must not say US2a incoming or US2b are finished (Days 9-11, Meeting 6). US1a moves to Done at Meeting 5. Remaining 0 only after Meeting 6 on Friday 23 October. Sprint 2 (US3b, US4a, US4b, US5b, US7, US8) is not Sprint 1 Done.